I approve

 the Chairman of the Board for Scientific Work and International Cooperation Yerzhanov N.T.:

2021

**PLAN**

Of work of the Innovation and Technology Park

"Ertis" for the 2021-2022 academic year

WORK PLAN FOR THE 2021-2022 ACADEMIC YEAR

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| n/a | Name of the events | Terms of use | Рerformers | execution control |
|  | 2 |  |  | 5 |
|  | Innovation and Technology Park "Erts" |
|  | Collection and analysis of information on scientific and technologicaldevelopments and projects for the purpose of "familiarization and possible application in educational and scientific activities | During the year | Dundukov M.M. Sultanov I.S. Dosmagulov K.J. | Isenov J.S. |
|  | Work with the teaching staff (PIIG)of the University for the organization of scientific and technical activities | During the year | Suztanov I.S. | Isenov J.S. |
|  | Participation in exhibition events with the purpose of presenting the achievements of scientists of the University | During the year | Sultanov I.S. | Isenov J.S. |
|  | Formation of a FabLab zone for conductingresearch activities | June 2021 | Dundukov M.M. | Isenov J.S. |
|  | Functioning of the University's laboratory complexes | September 2021 | Dundukov M.M. | Isenov J.S. |
| 6 | Creation, design and development of presentationmaterial on scientific inventions and technologies, research and scientific and technical catalogs of students and scientists | October 2021 | Dosmagulov K.Zh | Isenov J.S. |
| 7 | Participation in republican, regional andintra-university demonstration and exhibitionevents of innovative developments | During the year | Sultavov I.S. | Isenov J.S. |
| 8 | The number of students involved in studentresearch projects | November 2021. | Dosmagulov K.J. | Isenov J.S. |
| 9 | The number of laboratories equipped with moderntraining equipment for conducting classroomclasses on educational programs | September 2021 | Dundukov M.M. | Isenov J.S. |
| 10 | Providing laboratories with modern equipment | During the year | Dundukov M.M. | Isenov J.S. |
| 11 | Allocation of funds to provide laboratorieswith modern equipment and materials through public procurement, 2021 | November—December 2021 | Sultavov I.S. | Isenov J.S. |
| 12 | Preparation of the Department's annual report for the academic year | January 2021 | Дундуков М.М.Sultavov I.S..Dosmagulov K.J.. | Isenov J.S. |

 The director of ITP "Ertis" Isenov J.S.